FAIR (Re-)Commissioning (in 2018)
Strategy & Concepts
– Follow-up –
Ralph J. Steinhagen

---
… a FAIR amount of work ahead
2018
[Speaker Notes: The initial modularised start version is targeted to be commissioned and ready for physics by 2020. FAIR will extend and supersede the existing GSI accelerator facility which consists of the UNILAC – a general purpose linear accelerator, the SIS-18 synchrotron which will become the booster synchrotron for FAIR, the FRS Fragment Separator, and the Experimental Storage Ring ESR. Many of the FAIR experiments are either fixed-target experiments or experiments that are performed directly inside the storage ring. The SIS100 machine will become the new work-horse of FAIR. It's about 1 km long, a fast-ramping and super-conducting synchrotron that accumulates ions and protons from SIS18 and accelerates them up to a rigidity of about 100 Tesla-Meter. It has a six-fold symmetry, with most of the six long-straight sections being filled up by RF acceleration, bunch compression and bunch rotation systems, or devices related to injection and extraction such as kickers, electro-static and magnetic septa. Most of the SIS18 and SIS100 extraction options are tailored to either: * fast extraction or resonant third-order resonance extraction. We plan to using primarily the knock-out-exciter-based technique that continuously blows-up the beam emittance and pushes particles out of the stable phase-space separatrix.]

---
Fundamental Axiom
An accelerator is more than the sum of its parts:
Comissioning Procedures & Facility Exploitation
Personnel development & training
FAIR-MCR &
human-machine interfaces
FAIR-MCR
(“HKR”)
Control System:
LSA, Archiving/Logging, Performance Monitoring
Beam-Based Systems/BI Integration
(alignment, feedbacks, …), MCR Applications, ...
FC2WG
MPLs/MCs
...
magnets
instrumentation
RF
other HW systems
...
SW
HW
e.g SIS18
magnets
instrumentation
RF
other HW systems
...
e.g SIS100
magnets
instrumentation
Stripper
other HW systems
...
HEBT
magnets
instrumentation
RF
other HW systems
...
e.g. HESR
machine-to-machine
Interface
machine-to-machine
Interface
machine-to-machine
Interface
FAIR Users/
Experiments
Beam Commissioning
System Integration & Controls
Hardware Commissioning

---
FAIR Commissioning Procedure I/II
- Develop a (initial/re-)commissioning and operation strategy:
  - MoU between various stake-holders (AP, BI, CO, RF, ...)
    - define when, where and how the individual accelerator systems should fit in
  - Identify and define missing procedures, equipment and tools, e.g.:
    - define, check the need or priority of applications vs. 'use cases'
    - define, check integration and interface between specific equipment and CO/OP environment
  - Focus first on commonalities across then specifics within individual accelerators
    - MPLs/MCs define pace & resources of how fast to achieve the above
  - Dissemination/knowledge transfer from groups that constructed and performed the initial HW commissioning to the long-term operation
    - training of operational crews (physics, operation, tools, ...)
  - Scheduling tool for technical stops to follow-up possible issues found
*Procedure aims not only at the initial first but also subsequent re-commissioning e.g. after (long) shut-downs, mode of operation changes and/or regular operation
operational procedures

---
FAIR (Accelerator) Commissioning
Terminology & Structure
'Dry-Runs' & 'Machine Checkout':
- Focus on individual systems/devices
- Machine specific, aim at
  - generic system procedures (N.B. specifics part of FATs/SATs ↔ MPLs/equipment group responsibility)
  - specific schedule per acc. sector
- folded with:
  - acc. system availability (↔ equip. groups)
  - machine schedule (MC/MPLs)
- Traceability & Repeatability
Commissioning with Beam (BC):
- Focus on tracking beam progress through the along the beam production chain (BPC)
  - injection, circulating beam, ramp, …, extraction, target steering
- aim at generic procedures for all ring accelerators
  - supplemented by machine specifics where necessary (e.g. stochastic cooling, ...)
  - transfer-line considered as part of injection/extraction of previous/ following accelerator (cruicial overlap)

---
Example: FAIR Commissioning Procedures
https://fair-wiki.gsi.de/FC2WG/BeamCommissioning

---
Commissioning with Beam
Split Beam Commissioning into three stages:
  1. Pilot beams/”easily available” ions (e.g. U28+, Ar)
    - basic checks: threading, injection, capture, cool, convert, acceleration/decelerate, stripping & extraction
    - always done with 'safe' ie. low-intensity/brightness beam
      - Ions: simpler optics, beam dynamics → Protons: transition crossing
  1. Intensity ramp-up & special systems
    - achieving and maintaining of nominal transmission and beam losses
    - commissioning of e.g. e-cooler, slow extraction, transverse fast feedbacks
    - commissioning and validation of machine protection & interlock systems
    - Possibly unsafe operations always preceded by checks with safe beam
  1. Production operation with nominal intensities	(N.B. first time counted as 'commissioning' → later: 'regular operation')
    - push physics and beam parameter performance (emittance, momentum spread, ...)
    - identify and improve upon bottlenecks impacting FAIR's 'figure-of-merit
    - make fast setup and switch-over between different beam production chains routine

---
Commissioning Phases*
Phase	Description
A.1	Injection and first turn: transfer lines, injection commissioning; threading, initial commissioning beam instr.
A.2	Circulating pilot: establish circulating beam, closed orbit, tunes, RF capture
A.3	injection initial commissioning: initial commissioning of beam instrumentation cont'd, beam dump
A.4	Ramp: transition crossing (protons), control of orbit, Q/Q', ...
A.5	Injection & Extraction optics: beta beating, dispersion, coupling, non-linear field quality, aperture
A.6	Extraction: fast extraction, slow extraction, ...
A.7	Final Focus/Target Steering: transfer lines, final focus, internal/external target steering, ...
A.8	Preliminary physics runs: “physics” with intermediate safe beam parameter (experiment detector setup etc.)
A.9	Special aspects: special machine functions, e.g. stochastic/e-cooling, transverse FB, special RF manipulation
*inspired by commissioning and SW analysis efforts for LHC:
http://lhccwg.web.cern.ch/lhccwg/overview_index.htm
http://lhccwg.web.cern.ch/lhccwg/Bibliography/background-material.htm
http://proj-lhc-software-analysis.web.cern.ch/proj-lhc-software-analysis/
http://lhc-commissioning.web.cern.ch/lhc-commissioning/machine-checkout.htm

---
Preliminary Ideas for Dry-Runs I/III
- Organised per machine and/or group of accelerators/transfer-lines
- Tests per sub-systems, e.g.: technical services (controls network, electrical network, cooling and ventilation, access and safety systems), vacuum systems, power circuits (cryo & QPS (where applicable), powering interlocks, PC currents checked, low-level communication, ...), high-level controls (alarms, interlocks, cryo, post-mortem, archiving, equipment monitoring, remote device control, settings generation, …), timing system, MPS, radiation monitoring, pre-injector and transfer-lines, injection equipment, beam instrumentation, RF system, beam dump & collimation, experiments, … (list to be agreed upon)
- Within each sub-system: list of actual individual devices
  - link to system description (↔ control room level documentation)
  - tracking w.r.t. machine/system availability...
  - link to generic test procedure (OP view → HW specifics done as part of FAT/SAT)
  - summary of dry-run test results (+ document repetitions if necessary, last test/'good as of')
    - … not all test results are 'OK'/'not OK'. Need to discuss required level of detail.
  - Problems & issue tracking (↔ impact on beam commissioning)!

---
Preliminary Ideas for Dry-Runs II/III
Example: Power Circuits Checks
- Sequence, check (details need to be fleshed out):
  - supply of energy & utilities
  - low-level communication, On/Off
  - Tests with short & actual load (PC vs. circuit tests)
  - Test-ramps to Imin/Iref/Inom
  - Tracking performance → Ractual, Lactual → L(I) calibration, IDCCT calibration, ...
  - Iearth leakage, FFT(Imeas) → detects EMC issues, PC faults
  - state-machine tests (fault testing): interface to interlocks (FBAS), PC permit, …
  - SIS100/Super-FRS: quench training, circuit-quench via QPS, fast power abort, …
  - ...
  - availability of LSA (HWC) settings, ...
  - tests cycles
  - top-level applications, ...
Just a rough 1st-order example
Real-world LOEP input needed

---
Preliminary Ideas for Dry-Runs III/III
Open Questions:
- Traceability: poor-mans-solution acceptable for for small machines/few devices, e.g:
  - single Excel/OpenOffice/Wiki spread sheet for status tracking
  - detailed procedures in Wiki would do its job, how
  - Documentation of individual test results?
    - Screenshots? data blobs (files)?
  - How-to keep track of these results on the long-term? DB? EDMS? …?
- Repeatability: how-to track tests that were done or need to be redone (e.g. after next technical stop)
- Applications:
  - HWC Tracker (overall status)?!
  - Sequencer in MCR: ~ 20 power converter OK to test by hand, but FAIR > 100!!
  - Equipment monitor (time traces, prior to availability to 'Archiving System')
  - Larger machines would benefit from automation/proper record keeping → what could be done with a reasonable effort for 2017 (2019)?

---
Next Steps
- Plan & coordinate dry-runs in view of SIS18 re-commissioning in 2018
  - driven by SIS18 constraints & CSCO milestone plan and availability
  - tentative schedule:
    - start 6 month before scheduled commissioning with beam, frequency ramp-up
      - Dry-Runs: 1-2 days every month, follow-up of issues, increase frequency if necessary
      - Last two weeks 'Machine-Checkout' every morning (afternoon to follow-up bugs)
    - Availability of systems determine what will be tested during each dry-run
- Start developing beam commissioning procedure → tentative review by Q3/Q4-2016
  - FAIR commissioning & operation success depends on readiness of systems and people
  - Responsibility shared collectively → not a 'one man show' → active participation & volunteers needed → small activity groups, documentation on wiki
    - feel free to propose further participants you consider pertinent or whom it may concern
    - requirement for dissemination and impact on real-world FAIR operation

---
Comments? Questions?

---
SIS18 Efficiency
FAIR Challenges & Constraints
… SIS18 Operation Experience & Efficiency I/II
possibly pessimistic/simplistic1,2 estimate, control room experience:
  - presently: '~ 1 shift UNILAC setup + 1 shift SIS18+TL setup' ↔ 1-2 weeks of experiments
- 2014: Beam-on-Target (BoT) figure of merit (FoM) of ~70%
  - sufficient for present mode of operation (~20% HW failures, ~13% setup)
  - however: high losses/activation & FoM does not scale for FAIR
1possibly strong assumption that new machines can be operated with the same routine, ease and efficiency as the present GSI infrastructure, …	2complex beam chains (e.g. HESR) with long beam setup times are typically run longer/more static than shorter (SIS18 experiments)

---
FAIR Challenges & Constraints
… SIS18 Operation Experience & Efficiency II/II
FAIR-BoT (efficiency εFAIR):
  - further convoluted with HW failures, availability of infrastructure
%varepsilon_{"FAIR"} ~:=~ prod from{i} to{n_{machines}} %varepsilon_{i} ~=~~ %varepsilon_{"ESR/SIS18"} cdot %varepsilon_{"SIS100"} cdot %varepsilon_{"SuperFRS"} cdot %varepsilon_{"CR"} cdot %varepsilon_{"HESR"} cdot ...
“… room to improve!”