FAIR (Re-)Commissioning (in 2018)
Strategy & Concepts
Ralph J. Steinhagen

---
… a FAIR amount of work ahead
[Speaker Notes: The initial modularised start version is targeted to be commissioned and ready for physics by 2020. FAIR will extend and supersede the existing GSI accelerator facility which consists of the UNILAC – a general purpose linear accelerator, the SIS-18 synchrotron which will become the booster synchrotron for FAIR, the FRS Fragment Separator, and the Experimental Storage Ring ESR. Many of the FAIR experiments are either fixed-target experiments or experiments that are performed directly inside the storage ring. The SIS100 machine will become the new work-horse of FAIR. It's about 1 km long, a fast-ramping and super-conducting synchrotron that accumulates ions and protons from SIS18 and accelerates them up to a rigidity of about 100 Tesla-Meter. It has a six-fold symmetry, with most of the six long-straight sections being filled up by RF acceleration, bunch compression and bunch rotation systems, or devices related to injection and extraction such as kickers, electro-static and magnetic septa. Most of the SIS18 and SIS100 extraction options are tailored to either: * fast extraction or resonant third-order resonance extraction. We plan to using primarily the knock-out-exciter-based technique that continuously blows-up the beam emittance and pushes particles out of the stable phase-space separatrix.]

---
Commissioning – Plan of Action
Beware
joke!
FC2WG
Need to be more explicit w.r.t. 'item 4' for commissioning and operation of FAIR.

---
Summary
FAIR Commissioning & Control
– Summary, see also HIC4FAIR'2015
- FAIR facility shall continue to provide a high degree of flexibility
- Additional new challenges for FAIR:
  - higher energies, high-intensity operation, increased complexity, machine protection, minimising machine activation, … → control of particle losses becomes more important
  - beam becomes more sensitive to beam parameter changes, dynamic vacuum effects & magnet hysteresis → may change tune/orbit working point & impact slow extraction/losses, ...
- Main paradigm changes:
  - Need better control of hysteresis: decouple magnetic cycle from dynamic beam (extraction) request
  - Need beam intensity ramp-up concept
    - no injection of high-intensity beam into an 'empty' machine
    - settings need to be (re-)validated with increasing beam intensity and whenever magnetic pattern changes
  - Flexibility comes with some overhead costs → trade-off between 'flexibility' & 'beam-on-target' required
    - new complexity: larger accelerator chain → example next slide
    - caveat: mode of operation changes costs → trade-off between flexibility, machine availability, and beam-on-target
  - Need to limit of what can be setup in parallel
    - re-tuning of machine parameter & potential cross-talk with other beams for high-intensity beams
    - e.g. intercepting transfer-line diagnostics
- Main optimisation strategy/recipe, aim at:
  - quasi-periodic cycle operation
    - minimise major pattern changes by construction ↔ beam schedule planning (tools)
  - minimise overhead costs of changing beam patterns and context switches
    - optimise operation ↔ smart tools & procedures, e.g. beam-based feedbacks, sequencer, …
    - improved planning of commissioning & beam schedule
today's focus

---
SIS18 Efficiency
FAIR Challenges & Constraints
… SIS18 Operation Experience & Efficiency I/II
possibly pessimistic/simplistic1,2 estimate, control room experience:
  - presently: '~ 1 shift UNILAC setup + 1 shift SIS18+TL setup' ↔ 1-2 weeks of experiments
- 2014: Beam-on-Target (BoT) figure of merit (FoM) of ~70%
  - sufficient for present mode of operation (~20% HW failures, ~13% setup)
  - however: high losses/activation & FoM does not scale for FAIR
1possibly strong assumption that new machines can be operated with the same routine, ease and efficiency as the present GSI infrastructure, …	2complex beam chains (e.g. HESR) with long beam setup times are typically run longer/more static than shorter (SIS18 experiments)

---
FAIR Challenges & Constraints
… SIS18 Operation Experience & Efficiency II/II
FAIR-BoT (efficiency εFAIR):
  - further convoluted with HW failures, availability of infrastructure
%varepsilon_{"FAIR"} ~:=~ prod from{i} to{n_{machines}} %varepsilon_{i} ~=~~ %varepsilon_{"ESR/SIS18"} cdot %varepsilon_{"SIS100"} cdot %varepsilon_{"SuperFRS"} cdot %varepsilon_{"CR"} cdot %varepsilon_{"HESR"} cdot ...
“… room to improve!”

---
Global Requirements & Constraints
- Much larger facility, cannot reliably extrapolate from present 'UNILAC→SIS18→ESR' operation to requirements for FAIR (9+ resp. 13 accelerators, higher/unsafe intensities, more users)
- Will be in a constant flux of frequent adaptations to new cycles/beam parameters, etc. present estimate:
  - avg. experiment run: ~ 1-2 weeks + many new storage rings and transfer lines with high(er) complexity → machine setup time-scale
  - high-intensity operation requires more and better fine-tuning
    - dynamic vacuum, activation & machine protection (mainly septa, instrumentation, etc.)
  - limited operator resources: 4-5 (beam operation) + 1 (infrastructure, cryo)
→ need to be smart and develop an efficient commissioning procedure, training and tools to facilitate fast turn-around and maintain (or improve) present operational efficiency

---
Fundamental Axiom
An accelerator is more than the sum of its parts:
Comissioning Procedures & Facility Exploitation
Personnel development & training
FAIR-MCR &
human-machine interfaces
FAIR-MCR
(“HKR”)
Control System:
LSA, Archiving/Logging, Performance Monitoring
Beam-Based Systems/BI Integration
(alignment, feedbacks, …), ...
FC2WG
MPLs/MCs
...
System Integration & Controls
magnets
instrumentation
RF
other HW systems
...
SW
HW
e.g SIS18
magnets
instrumentation
RF
other HW systems
...
e.g SIS100
magnets
instrumentation
Stripper
other HW systems
...
HEBT
magnets
instrumentation
RF
other HW systems
...
e.g. HESR
machine-to-machine
Interface
machine-to-machine
Interface
machine-to-machine
Interface
FAIR Users/
Experiments

---
Control Core Topics
- Archiving – Follow-up:
  - summary and documentation (+ GSI/CERN discussion) on FC2WG wiki
  - second specification iteration by Q3-2015
  - CSCO: first technical implementation concept (S. Jülicher et al.) → Q3-2015 (??)
- Accelerator & Beam Modes – Follow-up:
  - summary and documentation on FC2WG wiki
  - specification iteration (confirmation) by Q3-2015
- Role-Based-Access (RBAC) & Management of Critical Settings (MCS) → to be addressed this year
  - Organise review + use-case-analysis
    - 1st iteration: small round and using SIS18/SIS100 as an example (KISS + efficient)
    - 2nd iteration: wider community → Q3-2016
    - 3rd iteration: early specification → Q4-2016 (realistic?)
- CO/SW Test-Bed Strategy
  - during construction phase: needed to facilitate dry-runs and GUI/FB developments before all HW systems are available/ready
  - during operation phase: (offline) OP Training during shut-downs & during H.I. operation (no/limited live training possibility)
  - During high-intensity operation: testing of new CO concepts ↔ optimisation of beam availability/minimise cross-talk with ongoing operation (CERN experience ...)
- Integration of BI/CO equipment into Beam-Based Semi-Automated Control Loops
  - via LSA, aka. 'slow cycle-to-cycle feedbacks'
  - need CO-SW developer-'accelerator expert' pairing, priority list & milestone planning → next slide

---
Beam-Based System Integration – Pairing I/II
Generic Priorities (ie. all machines)
… key to efficient and fast transitions between pattern and parallel operation!
Beam-Instrumentation (focus on HW)
- Overview and strategy (M. Schwickert, FCWG #4)
  - MP relevance, OP robustness, reliability, nice-to-have
- Group I: Intensity monitoring across + BLMs across transfer lines & rings (M. Sapinski, S. Damjanovic, FCWG #9)
- Group II: Orbit/Trajectory & Q/Q'
- Group III: Beam Loss & Vacuum
- Group IV: longitudinal diagnostics (bunch shape/length, splitting/merging, abort gap monitoring, tomography, ...)
- Group V: emittance diagnostics and preservation (after optics)
Machine Protection (focus on HW)
- High-intensity Operation (C. Omet, FC2WG #7)
- Fast Beam Abort System (M. Mandakovic, FC2WG #7)
Beam Control (focus on use-case)
1. Transmission Monitoring System (R. Steinhagen, FC2WG Meeting #6)
2. Orbit Control (work in progress)
Trajectory Control (threading, inj./extraction, ??)
1. Q/Q'(') Diagnostics & Control	(??)
2. RF Capture and (later) RF gymnastics (??)
3. TL&Ring Optics Measurement + Control (LOCO, AC-dipole techniques etc.,)
4. Longitudinal Emittance Measurement (?)
5. Transverse emittance measurement (?)
6. Transverse and longitudinal feedbacks (RF: ???)
Bread-and-Butter
systems for OP
~ ideally for SIS18 restart

---
Beam-Based System Integration – Pairing II/II
Machine Specific & Generic Systems
- Machine Specific Integration of Beam-Based Systems:
  - SIS18
    - Multi-Turn-Injection (N.B. highly non-trivial, complex subject)
    - Slow-Extraction (K.O. exciter, spill-structure, ...)
  - SIS100
    - Slow-Extraction (K.O. exciter, spill-structure, ...)
    - RF Bunch Merging and Compression
  - (Super-)FRS: tbd.
  - ESR, HESR & CR:
    - Stochastic cooling, Schottky diagnostics, …, tbd.
- Generic:
  - Remote Acquisition of Analog Signals → needs to be finalised by Q1-2017 (UNILAC ~ OK, SIS18, ESR!?!)
    - strong impact on HKR migration/operation!
  - Fixed-displays, Facility & Machine Status (“Page One”)
  - Context-based monitoring of Controls and Accelerator Infrastructure
    - electrical power network, power converter infrastructure, cryogenics & vacuum, other facilities: water, personnel safety radiation monitors, ...
    - controls and timing network (latencies, instantaneous/avg. bandwidth load), FE CPU/temperature loads
  - Tools for
    - check-out test analysis (SAT, passed, in-progress, fault)
    - availability analysis → e-logbook & error/fault/down-time tracking (→ probably LOAO)

---
Fundamental Axiom
An accelerator is more than the sum of its parts:
Comissioning Procedures & Facility Exploitation
Personnel development & training
FAIR-MCR &
human-machine interfaces
FAIR-MCR
(“HKR”)
Control System:
LSA, Archiving/Logging, Performance Monitoring
Beam-Based Systems/BI Integration
(alignment, feedbacks, …), ...
FC2WG
MPLs/MCs
...
System Integration & Controls
magnets
instrumentation
RF
other HW systems
...
SW
HW
e.g SIS18
magnets
instrumentation
RF
other HW systems
...
e.g SIS100
magnets
instrumentation
Stripper
other HW systems
...
HEBT
magnets
instrumentation
RF
other HW systems
...
e.g. HESR
machine-to-machine
Interface
machine-to-machine
Interface
machine-to-machine
Interface
FAIR Users/
Experiments

---
Re-working, re-optimisation is inefficient and costly
Proposal to follow a long-term strategy and 'TPS lean principles':
- Continuous improvement
  - Right processes to produce right results and for getting it right the first time
    - commissioning procedures as evolving operation standard
    - system integration: definition of what, how and when (prioritisation) is needed
  - Prevention of inefficiencies, inconsistencies & waste by design
    - 'poka-yoke' or 'error proofing' principle – culture of stopping and fixing
      1. early, when and where they occur (at the source)
      2. with low-intensity, low-quality or alternate* beam rather than with high-intensity beam
      3. addressing first basic parameters before complex higher-order effects
    - Example #1: first fix injection, trajectory, orbit, Q/Q' before addressing space-charge or slow-extraction problems
    - Example #2: important losses for low-intensity beam have larger impact for high-intensity beam (↔ activation)
- Respect for people – “develop people, then build products”→ FC2WG #1, S. Reimann
  - optimise operation ↔ smart tools & procedures, e.g. beam-based feedbacks, sequencer, …
    - automate routine task so that operator talents are utilised and focused on more important tasks
  - training, investment in and development of people – minimise overburden/strain of personnel
*N.B. alternate: e.g. commissioning the anti-proton beam lines and rings with protons”

---
FAIR Operation/Control Paradigm
S. Reimann FC2WG #1, 2015-05-21
'One Operator per Accelerator Domain' vs. 'One Operator per Experiment':
Operator #1
Operator #2
Operator #3
Operator #4
UNILAC
SIS18
SIS100
CR
Q1
SuperFRS
CR
Operator #1
Q2
pLinac
SIS18
SIS100
p-Target
CR
HESR
Operator #2
UNILAC
SIS18
SIS100
Q3
CBM
Operator #3
UNILAC
SIS18
SIS100
Q4
APPA
Operator #4
UNILAC
SIS18
FRS
CR
Q1
ESR
Cry-Ring
UNILAC
SIS18
Qn
ESR etc.

---
High-Intensity 2
High-Intensity Operation
Additional measures for safe and reliable high-intensity operation:
- Pilot-Beam Concept:
  - new injection into an empty/untested machine must always be preceded by a pilot (ie. low-intensity) beam to validate injection, orbit, Q/Q', ... extraction
  - rationale: prevent “discovering” failed HW, bad settings with (potentially un-safe) high-intensities
- Intensity-Ramp-Up Concept:
  - Highest-intensities (> ~1010 ppb) only after successful intensity ramp-up
  - Need to verify beam parameters after every major cycle (hysteresis) or setting changes (Q/Q' working point, optics)
  - rationale: staged verification of intensity-related parameters, shift of working points, settings and systems (ie. better to discover/analyse/mitigate losses at low than high intensities)
- Additional concept: 'Beam-Presence-Flag' & 'Setup-Beam-Flag'
  - improves machine availability for low-intensity (safe masking of interlocks) while guaranteeing safety for high-intensity operation
  - For details see: http://fair-wiki.gsi.de/FC2WG/

---
Beam Modes
FAIR Beam Modes – State Diagram
For details: http://fair-wiki.gsi.de//FC2WG
verification of machine-protection functionality
Minor adjustment of intensity related effects (e.g. ∆Q(intensity))
Intensity
Ramp-Up
tune beam parameters (within limits) to
suit the experiments needs/performance
Adjust
Pilot Beam
basic accelerator setup
injection->extraction
typically with (but not limited to)
low setup intensities (SBF=true)
“handshake”
Stable Beams/
Production
Post-Mortem/
Beam Dump
always
start here:
No Beam
Here'd be Happiness
producing physics beams
most settings locked-down
mag. cycles only
e.g. RF conditioning
Recovery:
No Beam
N.B.:
omitted arrows to 'No Beam'/'Pilot Beam'	for better visibility (always possible)
modes follow existing normal setup routine, initial transition acknowledged by operator, subsequent driven automatically by sequencer
normal operational path
error/fault case
low-intensity
cool down + cycling after
magnet quench or main PS failure
N.B. beam mode = machine mode
for low intensity

---
FAIR Commissioning Procedure I/II
- Develop a (initial/re-)commissioning and operation strategy:
  - MoU between various stake-holders (AP, BI, CO, RF, ...)
    - define when, where and how the individual accelerator systems should fit in
  - Identify and define missing procedures, equipment and tools, e.g.:
    - define, check the need or priority of applications vs. 'use cases'
    - define, check integration and interface between specific equipment and CO/OP environment
  - Focus first on commonalities across then specifics within individual accelerators
    - MPLs/MCs define pace & resources of how fast to achieve the above
  - Dissemination/knowledge transfer from groups that constructed and performed the initial HW commissioning to the long-term operation
    - training of operational crews (physics, operation, tools, ...)
  - Scheduling tool for technical stops to follow-up possible issues found
*Procedure aims not only at the initial first but also subsequent re-commissioning e.g. after (long) shut-downs, mode of operation changes and/or regular operation

---
FAIR Commissioning Procedure II/II
Distinguish two forms of 'commissioning':
  1. Hardware Commissioning (HWC)
    - Formal functional checks and acceptance tests of the physical objects
    - HW System integration into the controls/OP environment
    - Done during initial commissioning and as part of the 'machine check-out' after every (longer) technical stops (e.g. annual shut-down)
  1. Commissioning with Beam (BC)
    - thread, inject, capture, cool, accelerate, decellerate, convert, strip, and extract through the accelerator chain
    - commissioning of beam-dependent equipment

---
Hardware Commissioning
Covers two aspects:
  1. Initial hardware acceptance tests
    - Checks conformity with contractual design targets
    - Done once, or after major upgrade or modifications
      - mainly done by system responsible/experts
      - coordinated by machine project leaders
  1. 'Machine Checkout' – presently not covered (yet)
    - Checks conformity of system's controls integration and readiness for beam commissioning/operation
      - Checked during 'dry-runs' – periodic (partial) facility tests coordinated by CO/OP
    - Needs to repeated after every shut-down or longer technical stop
      - Presently done on a system-by-system basis
      - Would benefit from a more global approach
covered by present
project structure

---
Commissioning with Beam
Split Beam Commissioning into three stages:
  1. Pilot beams/”easily available” ions (e.g. U28+, Ar)
    - basic checks: threading, injection, capture, cool, convert, acceleration/decelerate, stripping & extraction
    - always done with 'safe' ie. low-intensity/brightness beam
      - Ions: simpler optics, beam dynamics → Protons: transition crossing
  1. Intensity ramp-up & special systems
    - achieving and maintaining of nominal transmission and beam losses
    - commissioning of e.g. e-cooler, slow extraction, transverse fast feedbacks
    - commissioning and validation of machine protection & interlock systems
    - Possibly unsafe operations always preceded by checks with safe beam
  1. Production operation with nominal intensities	(N.B. first time counted as 'commissioning' → later: 'regular operation')
    - push physics and beam parameter performance (emittance, momentum spread, ...)
    - identify and improve upon bottlenecks impacting FAIR's 'figure-of-merit
    - make fast setup and switch-over between different beam production chains routine

---
Scheduling
Dry-Runs & Commissioning with Beam (BC)
- Important aspects that need to be factored in:
  - efficiency evolution: early beam commissioning → reaching final beam parameter
  - dry-runs & BC (notably Stage I) are aimed at identifying issues early on
    - machine alignment, magnet/BI polarity issues, controls “features”, …
    - To note:
      - SIS18/ESR/.. have been offline/disassembled for one year
      - new controls system: concepts, FECs, data supply (LSA), user interfaces, …
      - operational challenges
 → require follow-up → should plan and pencil in some adequate time into the	beam schedule (technical stops, preliminary physics/calibrations runs, etc.)
- Rough scheduling proposal:
  - Short-term (BC stage I): ~ 3-6 month beam commissioning (day-shifts, 50%), limited parallel experiments (ie. nights & weekends)
  - Medium-term (BC stage II): few day shifts of beam commissioning/week (~15 - 20%), rest beam operation
  - Long-term (BC stage III): mainly beam operation, 1-2 days per 2-3 weeks for BC & MDs

---
Commissioning Phases*
Example I/II
Phase	Description
A.1	Injection and first turn: transfer lines, injection commissioning; threading, initial commissioning beam instr.
A.2	Circulating pilot: establish circulating beam, closed orbit, tunes, RF capture
A.3	injection initial commissioning: initial commissioning of beam instrumentation cont'd, beam dump
A.4	Ramp: transition crossing (protons), control of orbit, Q/Q', ...
A.5	Injection & Extraction optics: beta beating, dispersion, coupling, non-linear field quality, aperture
A.6	Extraction: fast extraction, slow extraction, ...
A.7	Final Focus/Target Steering: transfer lines, final focus, internal/external target steering, ...
A.8	Preliminary physics runs: “physics” with intermediate safe beam parameter (experiment detector setup etc.)
A.9	Special aspects: special machine functions, e.g. stochastic/e-cooling, transverse FB, special RF manipulation
*inspired by commissioning and SW analysis efforts for LHC:
http://lhccwg.web.cern.ch/lhccwg/overview_index.htm
http://lhccwg.web.cern.ch/lhccwg/Bibliography/background-material.htm
http://proj-lhc-software-analysis.web.cern.ch/proj-lhc-software-analysis/
http://lhc-commissioning.web.cern.ch/lhc-commissioning/machine-checkout.htm

---
Commissioning Phases*
Example II/II
- Defined for each phase:
  - Short description of should be achieved
  - Entry and Exit conditions – clear definition of handover specs
    - definition of must-have systems,
    - op. procedures (e.g. machine patrol)
    - List of systems to be considered “operational” afterwards
  - Machine setup:
    - optics, beam type, MP equipment in place
  - Procedure:
    - detailed 'cookbook': check list of individual steps (settings, gains, …)
    - Optional items e.g. for night-time shift or delayed by another item
  - List of possible problems and first-order remedies
  - Open questions/action items
  - References (!!) & Acronyms
*for examples (LHC context) see e.g:https://edms.cern.ch/cedar/plsql/project.info?proj_id=1027639877

---
Example: Injection and First Turn
- Need – entry conditions
  - HW/SW conditions: full machine check-out, dry-runs performed, technical services available, ...
  - Machine state: ion optics, beam parameters to be used, ...
- Procedure:
  - Injection preparation: check transfer line settings, timing, kicker & power supply statuses, ...
  - Commission last meters of transfer line: check magnet & pick-up polarity, rough optics checks, commission beam instruments, ...
  - ...
- Potential Problems & Mitigation:
  - Cannot thread beam (beam lost somewhere) → Causes: … Diagnostics: ... Remedies: ...
- Open Questions:
  - UNILAC to SIS18 timing: first turn definition, ...
- Have – exit conditions:
  - Fully commissioned screens/IPMs, can exclude BI/kicker polarity errors, ...

---
Example: Injection and First Turn
- Short description of should be achieved
  - Commissioning of the last section of the transfer line and the injection
  - First commissioning of key beam instrumentation
  - Commissioning of the trajectory acquisition and correction
  - Threading the beam around the ring (first turn)
  - Closing the orbit to be ready for phase A.2 (establishing circulating beam)

---
Entry & Exit Conditions
Entry conditions
- Full checkout and dry-run performed
- Technical services available
  - Controls network
  - Electrical network
  - Cooling and ventilation
  - Access and safety systems
- Vacuum system
  - Insulating vacuum (SIS100, Super-FRS)
  - Beam vacuum (machine)
  - Beam vacuum (experiments)
- Deliverables for the power circuits
  - Cryogenics, water cooling, …
  - Cryostat instrumentation
  - Powering interlocks
  - QPS and energy extraction
  - Power converter currents checked
  - Main lattice circuits (dipoles, quadrupoles, sextupoles) powered
  - Experimental magnets & compensators OFF
  - …
- High level controls, ...
- Timing systems, …
- Machine protection subsystems, …
- Radiation monitoring systems, ...
Exit conditions (Objectives)
- Commissioning of TK/HEST/HEBT segment end, injection and thread around ring
- Trajectory acquisition and correction commissioning
- Beam Instrumentation
  - BPM: acquisition, auto-triggered asynchronous mode, first polarity checks
  - Beam Screens/Grids: acquisition, profiles
  - ICTs & DCCTs: acquisition, first calibration cross-check.
  - BLM: acquisition, first adjustment of thresholds
- Measurements
  - Partial polarity and calibration error checks in correctors and BPMs – Priority 1
  - Dedicated polarity and calibration error checks in correctors and BPMs – Priority 2
  - Systematic kick/response optics measurements – Priority 2
  - Injection septa and bumper transfer functions checked – Priority 2
  - Dedicated aperture checks – Priority 2
  - Energy mismatch between previous injector and ring corrected to 0.1% – Priority 2
  - Sextupoles polarities checked – Priority 2
- Machine Protection
  - FBAS operational with all beam and injection permits
  - MASP operational with all beam and injection permits
  - Safe Machine Parameters for beam injection permits (SBF, BPF)
  - (SW) Interlock system operational with all beam permits
- Controls & Applications
  - BI data acquisition, applications, displays and archiving
  - Sequencer, Accelerator & Beam mode state-machine ready
  - Post-Mortem: shot-by-shot beam quality for injection
- Injection System, ...
- Magnets, ...

---
Next Steps
- Iterate/agree on structure/terminology:
  - HWC (dry-runs)
    - SAT → MPL/MC domain
    - Dry-run – last 6 month before commissioning with beam (BC)
  - BC stages I, II, II
    - BC phases (A.1 injection, …)
- Plan & coordinate dry-runs in view of SIS18 re-commissioning in 2018
  - extend also to ESR & Cryring?
  - driven by SIS18 constraints & CSCO milestone plan and availability
  - tentative schedule:
    - start 6 month before scheduled commissioning with beam, frequency ramp-up
      - 1 day every month (TBC - 6...3 months)
      - 1-2 days every two weeks (TBC - 3 months – 2 weeks)
      - Last two weeks every morning (afternoon to follow-up bugs)
- Start developing beam commissioning procedure → aim at tentative plan in Q3/4-2016
  - Active participation & volunteers appreciated → small activity groups, documentation on wiki
    - Please feel free to propose further participants you consider pertinent or whom it may concern

---
Comments? Questions?

---
FCWG – Topics cont'd
- Commissioning in Stages:
  - HWC – Stage I: HWC & Machine Check-Out (S. Reimann/P. Schütt?)
    - power converter, RF, dry-runs, ...
  - HWC – Stage II: test-beds and what can we check w/o beam (J. Fitzek)
  - BC – Stage I: rough machine checkout (tbd.)
    - from injection through extraction, done with “pilot”/“probe”/safe beam intensities only:
      - “easily available” ions (U28+, Ar, etc.) – get particles through the chain (UNILAC→SIS18→SIS100)
      - protons: check transition crossing/avoidance scheme, etc.
  - BC – Stage II: higher intensities
    - e-cooler, space-charge effects, intensity ramp up
    - slow extraction, other machine specific features
    - Secondary particle recapture (p & SFRS targets) into CR → HESR
  - BC – Stage III: increasing intensity/high-intensity proton operation
    - Tighten screws on interlocks, collimation and OP procedures
    - fine-tuning of working point
    - Shift to regular day-to-day operation

---
Super Cycles at GSI: SIS18
Super Cycles at GSI: SIS18
- Cycles are stand-alone
- Template determines
  possible execution sequences
- Beam requests determine
  actual execution sequence
Time honored, but two major flaws:
Unpredictable magnetic history
  - frequently leads to beam degradation
  - empty cycles needed, wasting duty cycle
Next cycle not known
  - time for preparing transfer lines lost
  - sometimes leads to beam degradation
  - unnecessary idle time for long chains
Needs to be changed for FAIR...
Super cycle template
Possible execution sequences
Cave B
ESR
Cave A

---
Dynamic Magnet Effects
Dynamic Magnet Effects
Mostly iron dominated magnets
  - hysteresis (memory) effects
  - eddy current effects
  - reproducible for known history
  - impact on cycles:
    - critical for multi-turn injection & slow extraction
    - less critical for bucket-to-bunch transfer & fast-extraction
Possible procedural cures
  - choice of cycle sequence
    1. periodic patterns to fix history
    2. conditioning ramps to avoid hysteresis	(e.g. ESR low rigidity experiments)
    3. conditioning cycles for clean history (ie. for PP)
  - modification of settings during setup
    - parameters for compensation of hysteresis
    - add. dead-time for eddy-current decay
    - field corrections based on beam-based feedbacks	and measurements
Hysteresis compensation
Conditioning ramps
Conditioning cycles

---
Beam Production Chain & Patterns
Beam Production Chains & Patterns
- Beam-Production-Chain:
  - organisational structure to manage parallel operation and beam transfer through FAIR accelerator facility
  - defines sequence and parameters of beam line from the ion-source up to an experimental cave (e.g. APPA, CBM, SuperFRS, ...)
  - definition of target beam parameters (set values): isotope, energy, charge, peak intensity, slow/fast extraction, …
- Beam Pattern:
  - grouping of beam production-chains that are executed periodically
  - can be changed of pattern within few minutes (target, requires automation for beam-based retuning)
→ decouple beam request from magnetic cycle
  - now: dynamic user beam request → magnetic cycle → beam injection
    - random magnetic cycle ↔ non-reproducible hysteresis
  - FAIR: pre-programmed magnetic cycle + dynamic user beam request → beam injection
    - optimises magnetic pattern ↔ reproducible hysteresis
    - N.B. beam extraction still programmed ad lib by experiments
courtesy D. Ondreka
Chains
SIS18
SIS100
HESR
SIS18
SIS100
HESR
Pattern
SIS18
SIS100
HESR

---
Beam Production Chain Example 1
Beam Production Chains & Patterns
Example I/II
- Periodic beam patterns, dominated by one main primary experiment
  - example: p-production in HESR
- Secondary experiments fill gaps to optimise facility/accelerator duty cycle
- additional cycles to setup future beam requests or test new accelerator concepts or parameter (working points)
- Important: maintain pattern as long as reasonably possible ↔ hysteresis

---
Beam Production Chain Example 2
Beam Production Chains & Patterns
Example II/II
Periodic beam patterns, dominated by one main experiment:
courtesy D. Ondreka
SIS18
SIS100
Unilac
CBM + RIB ext. target (U73+) + AP (LE)
SIS18
SIS100
Unilac
ESR
RIB ext. target (U28+) + ESR
AP + RIB ext. target (U28+) + Biomat
SIS18
SIS100
HESR
Unilac
SIS18
SIS100
Unilac
ESR
RIB ext. target (U28+) + ESR
SIS18
SIS100
Unilac
CBM + RIB ext. target (U73+) + AP (LE)
AP + RIB ext. target (U28+) + Biomat
SIS18
SIS100
HESR
Unilac

---
Non-Tunnel HW Topics
to be discussed/decided
- FCT or DCCTs
  - Generation of 'Beam-Presence-Flag' & 'Safe-Beam-Flag' → masking of interlocks/fast-abort-signals
  - time-scale: few ten to hundred milliseconds before extraction
  - option: transmission monitoring? (dI/dt “Interlock”)
- BLMs + cryo-collimator→ integration into fast beam abort
  - time-scale: milliseconds → few turn (?, tbd.)
  - Rationale:
    1. protection of sensitive equipment
      - e.g. electro-static septum, slow-extraction/spill abort (transients)
    1. redundant MP element
      - “second line of defense” in case other MP measures fail
    1. High-Intensity Operation: control of transmission, activation (ALARA)
      - BLMs much more sensitive than FCT/DCCTs at high-intensities
    1. Quench prevention – tbd. ???
  - Idea: could also protect against transients during slow-extraction
- Other BI derived interlocks?
- SIS18/SIS100 BPMs → add. RF-Hybrid & RF-LP-Filter
  - improve robustness (bunch length/shape, intensity variations, less dependency on VGAs, ...)
  - better performance for injection steering & optics measurements (AC-dipole technique)
    - Trade-off: BPMs sensitivity (~1 (now) → 0.1 mm (target)) vs. larger K.O./TFS exciter kicks (δ ≈ 8-16 μrad @ injection)