2018 Recommissioning & Dry-Run Strategy and Planning
Ralph J. Steinhagen, S. Reimann, D. Severin for the FC2WG
*
* based on 2015/16 FC2WG presentations & meeting minutes

---
An attempt on defining a ...
FAIR Figure of Merit
Integrated Luminosity per experiment
Primary FC2WG goals:
efficient operation
better & safe beam control
… across the whole accelerator facilitiy
Experiment constraints:
dNions/dt constant (spill-structure)
dNions/dt|max constraints
...
beam brightness: Nions & εx,y,s
x 10-100 higher intensities Nions
x 10 beam energies
→ new:
machine protection
activation/loss minimisation (ALARA)
FAIR efficiency (simplified):

---
SIS18 Efficiency
SIS18 Operation Experience & Efficiency
1995-2016: U. Scheeler, S. Reimann, P. Schütt et al.
simple1,2 estimate, but relates to qualitative control room experience:
  - presently: '~ 1 shift UNILAC' + '1 shift SIS18+TL setup' ↔ 1-2 weeks of experiments
  - potential target after 2-3 years of FAIR operation:
    - simple experiments (e.g. attached to SIS18/SIS100): 1-2 shift setup ↔ 1-2 weeks beam-on-target
    - more complex experiments (e.g. at HESR): ~week setup ↔ months of operation (HESR),
- Need to factor in efficiency evolution: early beam commissioning → reaching final beam parameter
  - N.B. early SIS100-only availability indications (C. Omet et al.): 66 %
1possibly strong assumption that new machines can be operated with the same routine, ease and efficiency as the present GSI infrastructure, …	2 complex beam chains (e.g. HESR) with long beam setup times are typically run longer/more static than shorter (SIS18 experiments)
75% availability
for physics (incl. MDs)
12% operation
13% down-time
2007-2016

---
Accelerator Experience & Efficiency
1995-2016: U. Scheeler, S. Reimann, P. Schütt et al.
constant
~ 75 ± 5 %
long-running “static”
experiments
Many || experiments
re-configuration ~ 1-2 weeks
→ FAIR base-line
*
Based on: U. Scheeler, S. Reimann, P. Schütt et al., “Accelerator Operation Report”, GSI Annual Scientific Reports 1992 – 2015 + 2016 (D. Severin)
https://www.gsi.de/en/work/research/library_documentation/gsi_scientific_reports.htm
N.B. ion source exchanges are factored out from UNILAC & SIS18 data (~ constant overhead)
Availability: experiments + detector tests + machine development + beam to down-stream accelerators;
Down-time: unscheduled down-time + standby; Operation: accelerator setup + re-tuning
* 2018 operation limitations:
only ½ UNILAC (w/o A3 & A4)
only 1 element in SIS18
Therapy Operation
(different accounting)

---
FAIR Challenges & Constraints
… SIS18 Operation Experience & Efficiency
Beam-on-Target figure of merit (FoM) of ~75% → FAIR-BoT (efficiency εFAIR):
%varepsilon_{"FAIR"} ~:=~ prod from{i} to{n_{machines}} %varepsilon_{i} ~=~~ %varepsilon_{"UNILAC"} cdot %varepsilon_{"SIS18"} cdot %varepsilon_{"SIS100"} cdot %varepsilon_{"SuperFRS"} cdot %varepsilon_{"CR"} cdot %varepsilon_{"HESR"} cdot ...
+ new operational challenges:
operating beyond present beam parameter envelope, x10-100 higher intensities, x10 higher energies → machine protection & losses/activation become an issue
“… have to improve!”

---
Plan of Action
Need to be more explicit w.r.t. 'item 4' for commissioning and operation of FAIR.
Beam Commissioning
Physics
Operation

---
FAIR Commissioning & Control WG
http://fair-wiki.gsi.de/FC2WG/
focus in 2016
focus in 2015
FAIR Commissioning & Control Working Group
platform to discuss, coordinate and work-out FAIR commissioning and operation
open to all who can participate and contribute to this subject!

---
FC2WG Control Topics
– more than “Control System” & Data Supply
- Facility & Interface Analysis
  - Procedures: HWC, HWC-'Machine Check Out', BeamCommissioning, BC-Stage A (pilot beams), BC-Stage B (intensity ramp-up), BC-Stage C (nominal/production operation) Beam parameters, FAIR performance model, optimisation, Accelerator & Beam Modes
- Beam Instrumentation & Diagnostics – System Integration
  - Intensity (DCCTs) & beam loss (BLMs) → Beam Transmission Monitoring System (BTM), trajectory & orbit (BPMs), Q/Q', optics (LOCO & phase-advance), longitudinal & transverse emittance (FCTs. WCM, screens, IPM, etc.), Δp/p, long. bunch shape (FCTs, Tomography), abort gap monitoring, ...
- Accelerator Hardware – System Integration
  - Power converter, magnets, magnet model, RF, injection/extraction kicker, tune kicker/AC-dipole, beam dump, collimation/absorbers, cryogenics, vacuum, radiation monitoring, k-modulation, machine-experiment interfaces
- Control System
  - Archiving system, analog signal acquisition, test-beds, timing, bunch-to-bucket transfer, cyber security, role-based-access, middleware, RT & Feedbacks, daemons
- Components
  - post-mortem, management of critical settings (safe-beam settings), machine protection, interlocks, beam quality checks, daemons, 'Page One', aperture model, ...
- Applications
  - Sequencer (semi-automated procedures), fixed-displays, ...
  - Beam-Based Applications, Cycle-to-Cycle Feedbacks & GUIs → second talk

---
FAIR Operation/Control Paradigm
Some important OP boundary conditions:
  1. Compared to GSI, FAIR facility size and complexity increases roughly by a factor 4
  2. Expect some improvement but 'Operator' & 'System Expert' will likely remain a scarce resource
One strategy item: 'One Operator per Accelerator Domain' vs. 'One Operator per Experiment':
UNILAC
SIS18
SIS100
CR
Q1
pLinac
SIS18
SIS100
SuperFRS
p-Target
CR
CR
HESR
Q2
UNILAC
SIS18
SIS100
Q3
CBM
UNILAC
SIS18
SIS100
Q4
APPA
UNILAC
SIS18
Qn
ESR etc.
Operator #1
Operator #2
Operator #3
Operator #4
Operator #1
Operator #2
Operator #3
Operator #4

---
Poka-Yoke (ポカヨケ) – 'Mistake-Proofing'
Poka-Yoke (ポカヨケ) – 'Mistake-Proofing'
- Origin:
  - to avoid (yokeru) inadvertent errors (poka)
  - industrial processes designed to prevent human errors
    - Concept by Shigeo Shingo: 'Toyota Production System' (TPS, aka. 'lean' systems)
  - minimise common mistakes, procedural errors, etc. affecting machine performance and protection
- Real-World Examples:
  - Polarity protection of electrical plugs	(e.g. phone, Ethernet cable)
    - SIS18 profile grid connectors
  - Procedures: e.g. ATM machine: need to retrieve card before money is released (↔ prevents missing card)
X / mm
A / a.u.
X / mm
A / a.u.

---
Poka-Yoke (ポカヨケ) – 'Mistake-Proofing'
Reaction-Time and Cost → “fix” errors early
Fix problems early, when and where they occur
- Minimises procrastination of errors: “Safety starts with safe habits”!
  - big losses with big intensities	→ bad (activation)
  - large losses with small intensities → probably OK? … No!
    - requires paradigm change!
  - Interdependence between beam parameter & systems
- Early indication of developing/not-yet-critical faults:
  - Post-Mortem analysis ('as good as new' SIL assurance)
  - Preventative maintenance
  - fix “domino effect” problems at the source not its symptoms
    - e.g. fix problems with low-intensity beam rather than with high-intensity beam (avoids revalidation of loss patterns, MPS setup, …)
    - e.g. fix basic accelerator parameters before moving on to higher-order effect (e.g. extraction/injection energy/trajectory → orbit → tune → chromaticity → optic → … → driving term s
time until the problem
was discovered/fixed
costs

---
≠
FAIR one-of-a-kind prototype,
pushing the ion intensity & other limits
Should maintain realistic goals
& strategy how-to reach them

---
FAIR Commissioning Procedure I/II
- Develop a (initial/re-)commissioning and operation strategy:
  - MoU between various stake-holders (AP, BI, CO, RF, ...)
    - define when, where and how the individual accelerator systems should fit in
  - Identify and define missing procedures, equipment and tools, e.g.:
    - define, check the need or priority of applications vs. 'use cases'
    - define, check integration and interface between specific equipment and CO/OP environment
  - Focus first on commonalities across then specifics within individual accelerators
    - MPLs/MCs define pace & resources of how fast to achieve the above
  - Dissemination/knowledge transfer from groups that constructed and performed the initial HW commissioning to the long-term operation
    - training of operational crews (physics, operation, tools, ...)
  - Scheduling tool for technical stops to follow-up possible issues found
*Procedure aims not only at the initial first but also subsequent re-commissioning e.g. after (long) shut-downs, mode of operation changes and/or regular operation

---
FAIR Commissioning Procedure II/II
https://fair-wiki.gsi.de/FC2WG/HardwareCommissioning/
Distinguish two forms of 'commissioning':
  1. Hardware Commissioning (HWC → SAT A)
    - conformity checks of the physical with contractual design targets,
    - || commissioning of individual systems & tasks ↔ MPLs/equipment group responsibility
  1. Commissioning with Beam (BC → “SAT B” … )
    - Commissioning of beam-dependent equipment
    - Focus on tracking beam progress through the along the beam production chain (BPC)
      - threading, injection, capture, acceleration and extraction
    - + 'Dry-Runs': pre-checks at the end of HWC in view of beam operation:
      - Checks conformity of system's controls integration and readiness for Commissioning with Beam
      - check as much control/system functionality without beam as possible
      - Machine ist put into a state assuming that beam could be injected into the ring/segment
        - unavailable devices/systems are at first ignored, noted down, and followed-up at a defined later stage
Terminology:
Dry-runs: a rehearsal of the accelerator performance/function, starting typically six month before the targeted real BC
needs to (partially) repeated after shut-down or longer technical stop with substantial modifications
initial frequency: 1-2 days every month
frequency increased depending on the outcome of the initial dry-run tests
Machine-Checkout: intense accelerator performance tests (e.g. machine patrols, magnet/PC heat runs, etc.), typically two weeks before BC
needs to repeated after every shut-down or longer technical stop
repeated also on the long-term during routine operation of existing accelerators (already existing procedures/usus for existing machines)

---
Dry-Runs for Accelerator
= equivalent of Pre-flight Checks in Aviation

---
Commissioning with Beam
https://fair-wiki.gsi.de/FC2WG/BeamCommissioning
N.B. not to scale
Split Beam Commissioning into three stages:
  1. Pilot beams/”easily available” ions (e.g. U28+, Ar)
    - basic checks: threading, injection, capture, cool, convert, acceleration/decelerate, stripping & extraction
    - always done with 'safe' ie. low-intensity/brightness beam
      - Ions: simpler optics, beam dynamics → Protons: transition crossing
  1. Intensity ramp-up & special systems
    - achieving and maintaining of nominal transmission and beam losses
    - commissioning of e.g. e-cooler, slow extraction, transverse fast feedbacks
    - commissioning and validation of machine protection & interlock systems
    - Possibly unsafe operations always preceded by checks with safe beam
  1. Production operation with nominal intensities	(N.B. first time counted as 'commissioning' or 'assisted operation' → later: 'regular operation')
    - push physics and beam parameter performance (emittance, momentum spread, ...)
    - identify and improve upon bottlenecks impacting FAIR's 'figure-of-merit
    - make fast setup and switch-over between different beam production chains routine

---
Example: FAIR Commissioning Procedures
https://fair-wiki.gsi.de/FC2WG/BeamCommissioning
Main focus for 2018
(re-commissioning, new CO)

---
Example: FAIR Commissioning Procedures
https://fair-wiki.gsi.de/FC2WG/BeamCommissioning
initial test in 2018

---
Recommissioning & Operation in 2018 I/II
https://fair-wiki.gsi.de/FC2WG/HardwareCommissioning/
G-Day** – Start Physics Operation
Start Beam-
Commissioning
HWC
MC
BC
Mixed BC
Detector Tests
Physics
Machine
Checkout
('MK' coordinated
Beam time)
Dry-Runs
N.B. not to scale
- 2 weeks
- 6 months
- Hardware Commissioning → coordinated by Sub-Project-Leaders & Machine Coordinators
  - link-existing facilities (GAF), upgrades, machine re-alignment, “SATs”, HW systems (equip. groups),
- Dry-Runs – for all machines post (possibly also UNILAC), each two days, fixed dates (↔ experts availability), starting:
  - Dry-Run #1 – 17.10.2017: CO-core: LSA, Timing System, Archiving System, SCUs, CO core application, …
  - Dry-Run #2 – 14.11.2017: as before + tbd.
  - Dry-Run #3 – 12.12.2017: as before + tbd.
  - Dry-Run #4 – 09.01.2018: as before + BI + related applications
  - Dry-Run #5 – 06.02.2018: as before + Experiments (proposal) + Machine-Experiment Interfaces
  - Dry-Run #6 – 20.02.2018: as before + AEG + “last-minute” checks
  - Dry-Run #7 – 06.03.2018: buffer
- Machine-Checkout – intensive “last minute checks” (N.B closed tunnel/machine):
  - UNILAC:	-1 month → BC- 'day 0'
    - patrols, heat runs: RF & power supply conditioning, ...
  - SIS, ESR, CRY: -3 weeks → BC- 'day 0'
    - patrols, heat runs: RF & power supply/AEG conditioning, safety systems: personnel safety, access system, legal ZKS & RP checks (§66 Abs. 2 StrlSchV), “very last-minute” checks/bug fixes: vacuum, power, BI, CO, ...
* in 2018: light-version w.r.t. commissioning of new machines
** “guaranteed” start physics operation (Plan A), no hick-ups, sacrificial buffer being activities related to 'Stage B'
Stage A* (2018)
~ 1 month (net, tentative)
Physics Operation
min. 3 months (??)
Stage B*
(buffer, prep. For FAIR)

---
Recommissioning & Operation in 2018 II/II
https://fair-wiki.gsi.de/FC2WG/BeamCommissioning
Start Beam-
Commissioning
G-Start** PAC-Physics Operation
~1 w
tbc.
1 week
~ 2 weeks
“MK”-coordinated
3-4 d
1 d
3 d
3 d
M
BC
TS
BC
TS
BC/MDs
TS
Physics
TS
Physics
TS
A
[..]
BC
Mixed BC/
Detector Tests
N
Mixed BC/Detector Tests + OP
Technical
Stop
Technical
Stop
N.B. not to scale
- Stage-A: Initial Beam Commissioning (BC): 2 dedicated 3 week@24h/7 BC blocks, main aim:
  - drive beam expeditiously through the Beam Production Chain: sources → synchrotrons & beam transfers → exp. targets & storage rings
  - check basic 'accelerator mechanics': threading, injection, capture, cool, convert, acceleration/decelerate, stripping & extraction
  - identify beam-related limitations: polarities, RF, beam instrumentation, machine alignment, effective physical machine aperture, ...
- Immediately followed by dedicated, scheduled Technical Stop (TS)
  - needed for follow-up of HW (tunnel) and SW issues (CO, …)
- Stage-A/B*: Mixed-BC, Machine-Development, Detector Tests (aka. “splash events” for experiments) & Operator Training
  - N.B. “old machine” but completely new CO, substantial modifications
- Physics operation: as promised/targeted nett 3 months (to be confirmed), grouped into 2-3 blocks interleaved with
  - TS: routine maintenance → increases overall availability, follow-up of OP/CO/equipment issues + major ion species/source changes
  - MDs: follow-up of beam physics issues, CO improvements (e.g. beam-based FBs), improve facility to reach nominal FAIR parameters
    - N.B. also better for guaranteeing smooth restart/picking-up of physics operation after technical stops (experts availability)
Stage A
~1 month (net, tentative)
Guaranteed Physics Operation
 N > 3 months (tentative)
Machine
Development
Machine
Development
Machine
Development
Stage A/B*
(buffer, prep. For FAIR)

---
Upcoming FC2WG Topics
- 2018 Controls Retrofitting
  - 'what changes' vs. 'what will remain the same'
- Digitisation of analog signals – mandatory pre-requisite for major MCR upgrade and move to new FCC (!!)
  - Clarification of which signals remain to be digitised after the CO Retrofitting for 2018
  - Choice of technology for remaining signals (CO, BI, HV, RF, …) → should aim at limited number of platforms
    - Probably open items: fast (10-100 MHz) level time- and frequency domain signals
- RBAC & Management-of-Critical Settings (MCS) kick-off
  - Initially concepts and required roles (ie. Operator, MP-Expert, BI-Expert, RF-Expert, …)
- Beam Transformer Integration & Beam Transmission System (in-kind) → review by FC2WG before SPLs' sign-off
  - Specification dead-line: soonish < Q3-2017
- BPM integration into CO/OP concepts → part of in-kind requirements → review by FC2WG before SPLs' sign-off
- Detailed Dry-Run Planning – starting from November (contacted already CO, RF, EPS, HV, BI)
- BLM/BTM Specification + Integration, dead-line: end-2016
- Kicker/Septa Integration → Q2-2018
- Java Application & FESA Training (~ 2016/2017)
- New LSA-based Control Systems → OP Training?!?

---
Yes we can!
FAIR, can we do it?
Yes, we can!

---
Appendix

---
FAIR Commissioning
*courtesy Volkswagen
Switch to Space-Shuttle/Apollo 11 Example
Automobile integration/prototype commissioning
 have negative connotation at GSI