Dry-Run Procedures
& 1st Sequencer Iteration
Ralph J. Steinhagen
* based on 2015/16 FC2WG presentations & meeting minutes

---
Accelerator Controls Retrofitting
GSI → FAIR Transition in 2018
Substantial increase of scope w.r.t. GSI:
- Power converter:
  - SIS18: ~ 45 → SIS100: ~250 converter
  - HEBT: + 542 converter (30 types!)
  - HESR: + 44 converter
- RF: SIS18: 3→7→ SIS100: 38 RF sys.
- BI:
  - SIS18/ESR: ~24 → FAIR: ~250 BPMs
  - HEBT: 309 new BI devices
+ ~numbers for HV, Cryo, Vacuum, TI, ...
2018
[Speaker Notes: The initial modularised start version is targeted to be commissioned and ready for physics by 2020. FAIR will extend and supersede the existing GSI accelerator facility which consists of the UNILAC – a general purpose linear accelerator, the SIS-18 synchrotron which will become the booster synchrotron for FAIR, the FRS Fragment Separator, and the Experimental Storage Ring ESR. Many of the FAIR experiments are either fixed-target experiments or experiments that are performed directly inside the storage ring. The SIS100 machine will become the new work-horse of FAIR. It's about 1 km long, a fast-ramping and super-conducting synchrotron that accumulates ions and protons from SIS18 and accelerates them up to a rigidity of about 100 Tesla-Meter. It has a six-fold symmetry, with most of the six long-straight sections being filled up by RF acceleration, bunch compression and bunch rotation systems, or devices related to injection and extraction such as kickers, electro-static and magnetic septa. Most of the SIS18 and SIS100 extraction options are tailored to either: * fast extraction or resonant third-order resonance extraction. We plan to using primarily the knock-out-exciter-based technique that continuously blows-up the beam emittance and pushes particles out of the stable phase-space separatrix.]

---
Commissioning without Beam
https://fair-wiki.gsi.de/FC2WG/HardwareCommissioning/
N.B. not to scale
Hardware Commissioning (HWC → SAT A)
    - conformity checks of the physical with contractual design targets,
    - || commissioning of individual systems & tasks ↔ MPLs/equipment group responsibility
Terminology:
Dry-runs: a rehearsal of the accelerator performance/function, starting typically six month before the targeted real BC
needs to (partially) repeated after shut-down or longer technical stop with substantial modifications
initial frequency: 1-2 days every month
frequency increased depending on the outcome of the initial dry-run tests
Machine-Checkout: intense accelerator performance tests (e.g. machine patrols, magnet/PC heat-runs, etc.), typically two weeks before BC
needs to repeated after every shut-down or longer technical stop
repeated also on the long-term during routine operation of existing accelerators (already existing procedures/usus for existing machines)

---
Commissioning with Beam
https://fair-wiki.gsi.de/FC2WG/BeamCommissioning
N.B. not to scale
Split Beam Commissioning into three stages:
  1. Pilot beams/”easily available” ions (e.g. U28+, Ar)
    - basic checks: threading, injection, capture, cool, convert, acceleration/decelerate, stripping & extraction
    - always done with 'safe' ie. low-intensity/brightness beam
      - Ions: simpler optics, beam dynamics → Protons: transition crossing
  1. Intensity ramp-up & special systems
    - achieving and maintaining of nominal transmission and beam losses
    - commissioning of e.g. e-cooler, slow extraction, transverse fast feedbacks
    - commissioning and validation of machine protection & interlock systems
    - Possibly unsafe operations always preceded by checks with safe beam
  1. Production operation with nominal intensities	(N.B. first time counted as 'commissioning' or 'assisted operation' → later: 'regular operation')
    - push physics and beam parameter performance (emittance, momentum spread, ...)
    - identify and improve upon bottlenecks impacting FAIR's 'figure-of-merit
    - make fast setup and switch-over between different beam production chains routine

---
Poka-Yoke (ポカヨケ) – 'Mistake-Proofing'
Reaction-Time and Cost → “fix” errors early
… minimise common mistakes, procedural errors, etc. affecting machine performance and protection.
→ Fix problems early, when and where they occur:
  - Minimises procrastination of errors
  - “Safety starts with safe habits”!
- Benefits of early indicators of developing/not-yet-critical faults:
  - Identification/isolation of faults during HWC/DryRuns (e.g. via Sequencer) fixes “domino effect” problems at the source not its symptoms:
    - HWC: parallel testing possible	→ resource control by SPL/equipment group
    - BC: predominantly sequential testing	→ limited/no resource control ↔ “fire-fighting”
  - Preventative maintenance
    - early indication of drifting parameters (e.g. slow thermal runaway of IGBTs)
    - group common/similar maintenance tasks rather planning for having react (minimises “fire fighting”)
  - Post-Mortem analysis ('as good as new' SIL assurance)
    - insures safety-integrity-level, minimises risk at the source before they escalate
    - minimises human-intervention – OP/expert has to handle errors that have not/cannot be automatically analysed by the post-mortem system
time until the problem
was discovered/fixed
costs

---
FAIR Commissioning Procedures
- Procedures verify that functional and ‘Detailed Specification’ requirements have been fulfilled → FAT, SAT but also importantly for Beam Operation
  - checks MoU between various stake-holders (AP, BI, CO, RF, ...)
    - define when, where and how the individual accelerator systems should fit in
  - identify loop-holes/missing critical functionality
  - identification/isolation of errors & regression testing
    - ie. minimises that errors fixed in the past are not being reintroduced
  - ensures that HW is largely/fully commissioned prior to BC/operation
    - N.B. HWC (testing in ||) vs. BC (testing predominantly sequentially)
  - (semi-)automation: better to ‘act’ than to ‘react’ → triangle of ‘work to be done’ vs. ‘required project timeline’ vs. ‘available resources’
  - traceability and documentation (for your peers, SPL/management, operation, …)
    - improve the quality of the project (QA)
- Test procedures describe the intention of what needs to be achieved
  - specifically not implementation or tool specific ie. implementation can be refactored without the need to change the intention of the test
  - terminology/hierarchy of: unit testing → integration testing → acceptance testing

---
Proposed Procedure Structure
- Description
  - test procedures describe the intention of what needs to be achieved
  - specifically not implementation or tool specific
- Entry Conditions
  - dependencies to other systems/conditions → reference to other test sequences
- Machine Setup
  - conditions to be checked beforehand
- Procedure – list of individual tasks
  - for each detailed testing step:
    - short-hand key for each step (e.g. ‘step A’, naming taken from DS document)
    - short description of what needs to be achieved (ie. a ‘one liner’)
    - acceptance criteria (either from DS or split into warning/error)
- Problems
  - be free to comment on (technical) concerns or potential issues
- Exit conditions
- Open Questions & Action Items
- References & Acronyms
  - where applicable, helps you with further QA documentation

---
Example: FAIR Commissioning Procedures
https://fair-wiki.gsi.de/FC2WG/BeamCommissioning
Main focus for 2018
(re-commissioning, new CO)

---
Example: FAIR Commissioning Procedures
https://fair-wiki.gsi.de/FC2WG/BeamCommissioning
initial test in 2018

---
Sequences & Tasks I/III – Implementation
- ‘Task’ = device class specific atomic test, e.g.
  - connectivity test, power ‘on’, power ‘off’, ...
  - actual vs. reference comparison, ...
- ‘Tasks’ can be assembled to ‘Sequences’ …
  ...which may also contain further sub-sequences:
- CO backbone technologies:
  - FAIR Archiving Systems → Documentation
  - LSA-based Settings Management → Reference & Data Supply
  - System- and Site-wide Digitisation of Analog Signals→ ‘actual vs. reference’ process monitoring
Task 1
Task 2
Task M
Task Sn.1
Task Sn.2
Task Sn.N
...
Sequence
Task S1.1
Task S1.2
Task S1.N

---
Sequences & Tasks II/III – Implementation
- What is provided by the sequencer frame-work:
- Level 1 tests (provided by the CO/equip. Group/machine experts):
abstract class AbstractSequenceImpl extends AbstractTaskImpl implements Sequence {
void exec() {
execPreUserCode(); // init communication to Archiving, LSA, Sequencer Service etc.
execUserCode();
execPostUserCode(); // reporting, etc.
 }
}
class FrontEndGenericConnectivityTest extends AbstractSequenceImpl implements Sequence {
// [..]
void execUserCode() {
addTask(new Task("prepare", "init device status handler", this, () -> {
        deviceConnection = new GenericStatusTest(deviceName);
}));
addTask(new SkippableTask("step1", "check simple IP connectivity", this, () -> {
        if (deviceConnection.isHostReachable(CONNECTIVITY_TEST_IP) == false) {
        throw new RawSequenceException("testCMW3get() - failed");
        }
    }));
// [..]
}
   // [..]
}

---
Sequences & Tasks III/III – Implementation
what the user needs to implement
class HwcTest1 extends AbstractSequenceImpl implements Sequence {
void execUserCode() {
addTask(new FrontEndGenericConnectivityTest(getParameter()));
addTask(new Task("step1", "description #1", seqReference, () -> {
task1(); // user/device-specific non-skippable atomic test operation 1
}));
addTask(new SkippableTask("step2", "description #2", seqReference, () -> {
task2(); // user/device-specific skippable atomic test operation 2
}));
[..]
}
void task1() {
// test SAT-A sub-procedure x.1, see specification... item ...
// [..], may throw Exception (or derivatives)
}
void task2() {
// test SAT-A sub-procedure x.2, see specification... item ...
// [..], may throw Exception (or derivatives)
}
}
Some examples to get a flavour of the targeted code style and flavour:https://www-acc.gsi.de/svn/applications/app-codesnippets/

---
Some Preliminary Test Hierarchy
seq_level
Interface & DB configuration (FESA, FESA → LSA, CDB, deployment version, meta-data, status/interlocks)
Connectivity tests (IP, DNS, CMW, CMW-NS, JAPC, ...)
0
- Some logstash meta-data keys (see: https://logstash.acc.gsi.de/):
  - Existing tags: program: ‘sequencer’, user_name, pid, ...
  - seq_device: e.g. device name, LSA property name, global function
  - seq_level: <0 … 4>, seq_task: <task/class name>, seq_sequence: <collection of tasks> (???)
  - seq_testID: unique identifier for given sequencer run (↔ multi-user, parallelism)
  - seq_test_start: <time-stamp>
CO/FEC specific
Power Converter
RF
HV
<MD>
...
<FGx>
<MX>
<new FESA>
<FG6>
1
HW specific
LSA Hierarchy (mapping completeness, drive, ...)
2
physics
modelling
LSA Top Level Tests
3
OP aspects

---
Sequencer Protocolling Example
https://logstash.acc.gsi.de/

---
Qualitative GUI Example
courtesy Vito Baggiolini

---
Reinventing the Wheel ...

---
SIS18 Power Converter Specification
(incl. FAT & SAT, 1985, aka. “AEG”)
Aus: “Spezifikation für die Stromversorgung der Magnete des Schwerionensynchrotrons SIS 18”,
GSI ‑ SIS ‑ SPEZ / 85 ‑ 27, 06. August 1985 (EP)
https://edms.cern.ch/document/1225471/2
… 90 pages (don’t have time during commissioning/dry-runs)
1/4th of main dipole PC:
x 4
[...]
I.2.2 Magnetstromzyklen und technische Daten
ΔI/I = ±2.5·10-4
ΔI = ±20 mA for I < 80 A
feedback group delay:
Δt ≈ 10 ms (target)
Δt < 20 ms! (worst case)
reference
actual
reference
actual
circuit parameters:
N ≈ 25 magnets + 3 Septa
RDC ≈ 7.04 mΩ / mag. + 2 x 18mΩ + 8.88 mΩ + Rcable
L(I) ≈ 22.2 → 15.5 mH / mag. + 2x 1.4 mH + 0.17 mH
Imin = 80 A
Imax = 3500 A
Ical = 75 A
dI/dt|max = 19 kA/s (was 8,2 kA/s)
[..]

---
Example: “AEG” Documentation
Power Converter Topology

---
Existing “AEG” SAT Description
https://edms.cern.ch/document/1225471/2
I.5.4.7.1	Nachweis der Forderungen der Magnetstromzyklen
Die Einhaltung folgender Forderungen ist durch Messung nachzuweisen (s. Bild I.2.2/2).
1. Stromgenauigkeit, bezogen auf Momentanwert, entsprechend Abschnitt 1.2.2: bei Imax & Imin
2. Langzeit‑Genauigkeit: Messung der analogen Führungsgröße und der Regelgröße nach Erwärmung auf Endtemperatur über einen Zeitraum von 24 Stunden mit Differential‑Voltmeter Siemens PM 4602 D oder Fluke Modell 887 AB
3. Welligkeit – Betrachtungszeiträume: 20 ms, 100 ms, 1 s
4. Übergang von Imin in den linearen Anstieg, Übergangszeit, Übergangsfunktion – bei maximalen dI/dt & bei 10% dI/dt| max
5. Stromanstieg:
  1. Regelverzögerung Δt; überlagerte Welligkeit – bei maximalen dI/dt & bei 10% dI/dt| max
6. Übergang Anstieg → Flattop: wie d)
7. Übergang Abstieg → Imin: Ausregelzeit – bei maximalen dI/dt & bei 10% dI/dt| max
8. Meßanordnung für d‑g)
  1. KO‑Bild der Führungs‑ und Regelgröße Oszillograf mit Komparator‑Einschub Tek. 7A13 bzw. Differenzverstärker‑Einschub Tek. 7A22
I.5.4.7.2	Nachweis der Verluste [..]
I.5.4.7.3	Nachweis des Blindbedarfs [..]
I.5.4.7.4	Nachweis der Oberschwingungsströme [..]
I.5.4.7.5	Nachweis des Stromstoßes bei Einschalten des Transformatoren [..]
I.5.4.7.6	Nachweis der Rückwirkungen auf das 380 V‑Netz von GSI [..]
I.5.4.7.7	Nachweis der Erfassung des Isolationswiderstandes bzw. des Erdschlußstromes [..]
+ Controls Integration, Synchronisation with Timing System, Interlocks, ...
maybe spec requires just a bit of checking/dusting
… otherwise a good basis as commissioning procedure!

---
“Cathode Ray-Tube Picture”
TEK 7A13 & 7A22 (retired/not serviced by Tek since 1992)

---
Main Aims for FAIR
Prototyping at SIS18 Recommissioning in 2018
Sequencer – range of functionality:
  1. logging and protocol of executed tests → aim at 100% test coverage
  2. (semi-)automated test sequences (‘unit-style HW testing)
  3. user-driven execution and configuration of test sequences (by non-Java equipment experts)
- next steps:
  - review/collect additional functional requirements
  - support test procedures together with equipment groups
    - main responsibility remains with equipment experts (EPC, CO, BI, …)
    - priorities: 1. EPC, 2. HV (Septa & Kicker), 3. Ring-HF (rational: large quantity, (fairly) low complexity).
    - other equipment test-procedures (besides connectivity tests) require additional man-power (CO, vacuum, BI, ...).
  - support/drive Sequencer development
    - initial proof-of-concept for Dry-Run #1 covering:
      - ‘a)’ logging: inititally file-/logstash-based → Archiving System
      - ‘b)’ using simple Java based sequences executed via Eclipse (Java-expert only)
    - extend to covering also ‘c)’ requirements by Q1-2017 (on a ‘best effort’ basis)
      - initial aim: simple non-configurable GUI that can execute pre-defined test-sequences by non-Java/Eclipse-affine equipment experts
  - Follow-up of system- and machine commissioning procedures (with & w/o beams) → prerequisite for any sustainable system integration and accelerator facility operation

---
Next Steps I/II
- responsibility of the HW commissioning (SAT) as well as follow-up of the integration lies ultimately (as always) with the equipment group experts & SPLs
  - covers: HWC → SW integration → functional integration/acceptance tests, up to handing it over to regular operation
  - still, that doesn’t mean that one has to do everything alone→ other colleagues are there to support/help where necessary with the details – prerequisite: (SAT/Dry‑Run) commissioning procedure specific to your system
- Commissioning Procedures – Next Steps:
  - register yourself and get a user account on the FAIR wiki: https://fair-wiki.gsi.de/System/UserRegistration
  - draft a tentative commissioning/Dry-Run procedure
    - can be based on existing documentation, previous documents, or best practice
    - KISS: focus on content & functional test procedure steps – this is not supposed to be a legal text but understood by your (external) colleagues/partners/reviewers – ‘A good picture/diagram is worth a thousand words’
    - N.B. this would provide also a good basis of the functional/operational documentation
    - N.B. please keep non-german speakers in mind, use accepted common industry terminology, ISO, IEEE standards etc.
  - iterate with your immediate and affected peers (please keep R. Steinhagen and S. Reimann in the loop)
  - upload the procedure to the FC2WG Wiki don’t worry too much about format etc. (will take care of the format editing/links etc.)

---
Next Steps cont.
Semi-automated Test Sequences
- Prerequisite: arrange for an import of your to be tested devices into LSA (N.B. also a requirement for MASP and other CO applications)
  - notably missing: VAC, motor/compressed-air--drive controls, BI, …
- coding should start only after the commissioning procedure is in a good shape/has been established
  - (informal) agreement between key stakeholders (SPLs, SYS, CO, ...)
  - N.B. disclaimer: unless you code yourself and the sequence source code is the documentation by itself (OK for 2018 … only)
- Will organise a small mini-workshop on sequence-development for those who are willing to contribute/help with the procedures/test sequences → let yourself be known
- Tracking/documentation of the test execution will be done intrinsically by the Sequencer frame-work (via Archiving System), pending:
  - GUI for non-java-expert → best effort, … target ~Q1-2018
  - Analysis tools, graphical preparation of Dry-Run statuses and progress, … target for a rough first draft: Q1-2018

---
Appendix

---
FAIR Commissioning & Control WG
http://fair-wiki.gsi.de/FC2WG/
FAIR Commissioning & Control Working Group
platform to discuss, coordinate and work-out FAIR commissioning and operation
open to all who can participate and contribute to this subject!
System Integration
Commissioning w/o Beam (HWC/Dry-Runs)
Commissioning with Beam

---
Struktur FAIR
GSI x 2 (2,3)
Migration Strategy
GSI 3 → FAIR 8½ (11+) accelerator(-like) machines
p-Linac
SIS 18
SIS100
SIS 300
UNILAC
EH
EX
FRS
APPA
p-bar
SFRS
CBM
existing:
3 Ion-Sources
1 LINAC
1 synchrotron + 1 storage ring
13/7 transfer-lines (MEBT / HEBT)
3 experimental areas
ESR
CR
NESR
Cry-
Ring
HESR
(PANDA)
FLAIR
new:
1 proton source + linac
4 synchrotrons & storage rings
18 (26) transfer-lines
4 (5) experimental areas
MSV 0-3
MSV 4-6

---
FAIR Challenges & Constraints
… SIS18 Operation Experience & Efficiency
Beam-on-Target figure of merit (FoM) of ~75% → FAIR-BoT (efficiency εFAIR):
%varepsilon_{"FAIR"} ~:=~ prod from{i} to{n_{machines}} %varepsilon_{i} ~=~~ %varepsilon_{"UNILAC"} cdot %varepsilon_{"SIS18"} cdot %varepsilon_{"SIS100"} cdot %varepsilon_{"SuperFRS"} cdot %varepsilon_{"CR"} cdot %varepsilon_{"HESR"} cdot ...
+ new operational challenges:
operating beyond present beam parameter envelope, x10-100 higher intensities, x10 higher energies → machine protection & losses/activation become an issue
“… have to improve!”

---
Reliability Engineering I/III
predictive maintenance or ‘as good as new’ checks
Problem definition: classical bath-tub curve – in an ideal/naїve world:
we want to
continuously
operate here...
… but end up
eventually here

---
Reliability Engineering II/III
predictive maintenance or ‘as good as new’ checks
- Common improvement options: choice of materials, safety margin in material/parameter properties & adding redundancy
- However: redundancy provides only limited reliability gain → key to high reliability: performance surveillance + checks → ‘as good as new’ system validation
  - technical implementations at FAIR: Sequencer & Post-Mortem System

---
Reliability Engineering III/III
predictive maintenance or ‘as good as new’ checks
Sequencer (OP triggered) and Post-Mortem (MP triggered) checks
HWC
Dry-Runs→
Beam Commissioning
Re-Comissioning (with & w/o beam)
after Technical Stops & Post-Mortem

---
Facility Complexity & the Human Factor
Thinking Fast and Slow & “Human Multitasking”
Kahneman studies1 famously described the two different ways of our brain works and forms thoughts	(N.B. → awarded the 2002 nobel prize):
- System 1: “Fast”, automatic, frequent, emotional, stereotypic, subconscious.
  - role: assess the situation, deliver updates
  - based on past experience, intuition and learned experience
  - prone to cognitive bias, logic faults
  - Saves “mental energy” → usually preferred
- System 2: “Slow”, effortful, infrequent, logical, calculating, conscious.
  - role: seeks new/missing information, makes decisions
  - Can keep only up to five aspects in active memory
  - Requires (sometimes significant) ‘mental energy’ → unfavoured
… performing multiple complex, high-risk tasks is a actually very bad idea
→ unnecessary strain on operators, machine experts and operational risk
1Daniel Kahneman, “Thinking, Fast and Slow”, Farrar, Straus and Giroux, 2011